## Slide 1
Autonomous Intersection Management
Ahmed Fayed & Alex Winger

## Slide 2
Project Scope & Schedule
4-way 3-dedicated-lane intersection with a centralized architecture and minimum V2V communication.
No communication failure, delay, or execution error
We are using ROS and RVIZ for visualization.
Schedule:
  Revamped the AIM skeleton by Oct 9th
  Convert MATLAB code into Python & use ROS
  Have the system back up running to its previous state by Oct 25th
  Visualization & Reservation system modes by last Friday Nov 1st
  Remaining 5 weeks to devise a (hopefully) better policy and compare its efficiency.

## Slide 3: Progress & Challenges
Finished converting MATLAB code to Python
    Traffic generation, collision detection, car management
    Challenges: Code was not robust and needed to be redesigned more than we expected
  Developed simple visualization for testing
  Implemented Dresner/Stone and stop sign policies.
    Challenges: More advanced traffic light policy has taken more time to formulate
  Adaptive Cruise Controller
    Challenges: A more advanced ACC is needed to guarantee safety requirements

## Slide 4: Changes & Measures of Success
Porting the system was not as clean-cut as predicted
Developing a stress testing traffic generation technique
Pushing back about a week on milestones
When would the project be successful?
  Comparing efficiency (delay) between different modes
    Traffic Lights
    Stops Signs
    Dresner & Stone’s policy
    Our policy
  Our policy should at least provide shorter delays than current Traffic Light and Stop sign systems